## Sheet1
General Project Information
|  | Project Name | FC; Learining System
|  | sprint time | 2week
|  | scrum master | Yahia Mohamed
|  | Stakeholders | anyone want E- learning
|  | Expected Start Date | 2018-03-01
|  | Expected Completion Date | 2018-05-29
|  | product owner | E-learing company
|  | Budget | 15000$
Planning | Name | Story | Priority | Status | Analysis | Responsible | Design | Responsible | Implementation | Responsible | Testing | Responsible | Start | End | Days
Sprint 1 | Home page |  | High | Complete | [8 empty] | 2018-03-01 | 2018-03-15 | 14
Feature 1 | home | as a :user I want to:enter to website so that: know website body | High | Complete | analysis what home have | abdallah | design home | amr | coding home | mohamed galal | testing the page | mohamed gaber | 2018-03-01 | 2018-03-08 | 7
task1 | header | as a :user I want to:enter to home so that: know website kind | High | Complete | analysis what the head have | abdallah | design the head | amr | coding head | mohamed galal | testing the head | mohamed gaber | 2018-03-01 | 2018-03-04 | 3
task 2 | body | as a :user I want to:enter to home so that: show what website have | High | Complete | analysis what the body have | abdallah | design the body | amr | coding body | mohamed galal | testing the body is correct | mohamed gaber | 2018-03-04 | 2018-03-08 | 4
Feature 2 | search | as a :user I want:enter to search field so that: search about courses | Medium | Complete | analysis how the search would be | abdallah | design how the search would be | amr | coding search | mohamed galal | testing that the search work | mohamed gaber | 2018-03-08 | 2018-03-15 | 7
Sprint 2 | Courses |  | High | In Progress | [8 empty] | 2018-03-15 | 2018-03-29 | 14
Feature 3 | course | as a :user I want:enter to website so that: watch courses | High | In Progress | analysis whatcourses have | yasser | design home | amr | coding home | abdallah | testing the page | mohamed gaber | 2018-03-15 | 2018-03-22 | 7
task 1 | watch | as a :user I want:enter to courses so that: watch course | High | In Progress | analysis where the course shown | yasser | design the course design | amr | coding courses | abdallah | testing the course | mohamed gaber | 2018-03-15 | 2018-03-18 | 3
task 2 | comment | as a :user I want:enter to course so that: leave a comment | High | In Progress | analysis the comment seem | yasser | design the shape of comment | amr | coding comment | abdallah | testing the comment send | mohamed gaber | 2018-03-18 | 2018-03-22 | 4
Feature 4 | instructor | as a :user I want:enter to page so that:info instructor | Medium | Not Started | analysis info instructor | yahia | design the instructor shape | amr | coding the instructor page | mohamed galal | testing the page | mohamed gaber | 2018-03-22 | 2018-03-29 | 7
task 1 | name | as a :user I want:enter to page so that:know name of instructor | Medium | Not Started | analysis the instructor names | yahia | design the instructor name shape | amr | coding the instructor name | mohamed galal | testing database | mohamed gaber | 2018-03-22 | 2018-03-26 | 4
task 2 | career | as a :user I want:enter to instructor page so that:know career of instructor | Medium | Not Started | study the career of them | yahia | design the shape of them career | amr | coding the career | mohamed galal | testing the comment send | mohamed gaber | 2018-03-26 | 2018-03-29 | 3
Sprint 3 | Entering to page |  | Medium | Not Started | [8 empty] | 2018-03-29 | 2018-04-12 | 14
Feature 5 | login | as a :user I want:enter to website so that: watch the courses | Medium | Not Started | analysis what the login contain | abdallah | design the login shape | yahia | coding the the page content | yahia | testing the code effciency | yasser | 2018-03-29 | 2018-04-05 | 7
task 1 | form | as a :user I want:enter my data so that: do submit | Medium | Not Started | analysis what the form contain | abdallah | design the form | yahia | coding the form | yahia | testing the form working | yasser | 2018-03-29 | 2018-04-02 | 4
task 2 | submit | as a :user I want:click to submit so that: login | Medium | Not Started | analysis what the submit will do | abdallah | design the button of login | yahia | coding button,connecting with data base | yahia | testing that it check on database | yasser | 2018-04-02 | 2018-04-05 | 3
Feature 6 | signup | as a :user I want:make account so that: watch the courses | Medium | Not Started | analysis what the signup contain | abdallah | design the signup shape | yahia | coding the the page content | yahia | testing the code effciency | yasser | 2018-04-05 | 2018-04-12 | 7
task 1 | form | as a :user I want:enter my data so that: click submit | Medium | Not Started | analysis what the form contain | abdallah | design the form | yahia | coding the form | yahia | testing the form working | yasser | 2018-04-05 | 2018-04-08 | 3
task 2 | submit | as a :user I want:click to the button so that: make account | Medium | Not Started | analysis what the submit will do | abdallah | design the button of signup | yahia | coding the button and connecting with database | yahia | testing that it check on database | yasser | 2018-04-08 | 2018-04-12 | 4
Sprint 4 | Help |  | Medium | Not Started | [8 empty] | 2018-04-12 | 2018-04-26 | 14
Feature 7 | support | as a :user I want:enter to page so that:ask for help | Medium | Not Started | analysis what the support will do | mohamedglal | desing the page | amr | coding the page content | yahia | testing the page | mohamed gaber | 2018-04-12 | 2018-04-19 | 7
task 1 | information | as a :user I want:get som information so that: solve my problem | low | Not Started | analysis what the information will be | mohamedglal | design the list of information | amr | entering the data | yahia | testing the data is enough | abdallah | 2018-04-12 | 2018-04-15 | 3
task 2 | sending problem | as a :user I want:send a problem so that: get help | Medium | Not Started | analysis how sending the problem | mohamedglal | design the send problem form | amr | coding the form | yahia | testing that problem was send | abdallah | 2018-04-15 | 2018-04-19 | 4
Feature 8 | ContactUs | as a :user I want:enter data so that: contact with admin | Low | Not Started | analysis ways to make users contact us | mohamedglal | design the page content | amr | coding the page | yahia | testing the code effciency | mohamed gaber | 2018-04-19 | 2018-04-26 | 7
task 1 | form | as a :user I want:enter my data so that: click submit | low | Not Started | analysis what the form contain | mohamedglal | design the form | amr | coding the form | mohamed gaber | testing the form working | yahia | 2018-04-19 | 2018-04-23 | 4
task 2 | submit | as a :user I want:click to the button so that: contact with admin | low | Not Started | analysis what the submit will do | mohamedglal | design the button ofcontact us | amr | coding the button and connecting with database | mohamed gaber | testing that it check on database | yahia | 2018-04-23 | 2018-04-26 | 3
Sprint 5 | Additional |  | Low | Not Started | [8 empty] | 2018-04-26 | 2018-05-10 | 14
Feature 9 | buy courses | as a :user I want:enter to page so that: buy courses | Medium | Not Started | analysis the way to buy course | mohamedglal | desing the page | amr | coding the page | yasser | testing overall on the page | mohamed gaber | 2018-04-26 | 2018-05-03 | 7
task 1 | form | as a :user I want:enter my data so that: click submit | Medium | Not Started | analysis what the form contain | mohamedglal | design the form | amr | coding the form | yasser | testing the form working | mohamed gaber | 2018-04-26 | 2018-04-30 | 4
task 2 | submit | as a :user I want:click to the button so that: buy a course | Medium | Not Started | analysis what the submit will do | mohamedglal | design the button ofcontact us | amr | coding the button and connecting with database | yasser | testing that it check on database | mohamed gaber | 2018-04-30 | 2018-05-03 | 3
Feature 10 | logout | as a :user I want:close my e-mail so that: I watched the course | Low | Not Started | analysis how logout the website | yasser | design the button shape | mohamed gaber | coding the button | yahia | testing the button | amr | 2018-05-03 | 2018-05-10 | 7
task 1 | button | as a :user I want:click on logout button so that:get out from website | Low | Not Started | analysis what the button do | yasser | design the button shape | mohamed gaber | coding where he wii going | yahia | testing the button | amr | 2018-05-03 | 2018-05-10 | 7
Sprint 6 | Opinion |  | Low | Not Started | [8 empty] | 2018-05-10 | 2018-05-16 | 6
Feature 11 | Aboutus | as a :user I want:enter to page so that:know the owners | low | Not Started | analysis the page content | mohamedgalal | desing the page | amr | coding the page content | yasser | testing the page | mohamed galal | 2018-05-10 | 2018-05-13 | 3
task 1 | information | as a :user I want:get som information so that: know the owner of product | low | Not Started | analysis what information will be | mohamedgalal | design the list of information | amr | entering the data | yasser | testing the data is enough | mohamed galal | 2018-05-10 | 2018-05-13 | 3
Feature 12 | feedback | as a :user I want:enter my vote so that: give them my opinion | Low | Not Started | analysis how take feedback | mohamedgaber | design the page content | amr | coding the page | yasser | testing the code effciency | mohamed galal | 2018-05-13 | 2018-05-16 | 3
Sprint 7 | database |  | Low | Not Started | [8 empty] | 2018-05-16 | 2018-05-29 | 14
Feature 13 | login database | as a :user I want:enter my data so that:check my data and enter | low | Not Started | analysis how to check | yasser | desing the page | gaber | entering data | yahia | testing | mohamed galal | 2018-05-16 | 2018-05-20 | 4
Feature 14 | sing_up database | as a :user I want:enter my data so that: save it in data base | Low | Not Started | analysis how to save | yasser | design the page content | gaber | entering data | yahia | testing | mohamed galal | 2018-05-20 | 2018-05-23 | 3
Feature 15 | contactus database | as a :user I want:enter data so that: contact with admin | Low | Not Started | analysis how to save | yasser | design the page content | gaber | entering data | yahia | testing | mohamed galal | 2018-05-23 | 2018-05-29 | 7

## Sheet2
This sheet is to enable the drop-down lists
| High | Complete
| Medium | In Progress
| Low | Not Started