## Sheet1
Planning | Role | Responsible | Priority | Status | Start | End | Days
Home page | making the plan of project | yahia | High | Complete | 2018-03-01 | 2018-03-15 | 14
home | analysis what home have design the home with css implement the code of page test the page | yasser amr abdallah gaber | High | Complete | 2018-03-01 | 2018-03-08 | 7
search | implement html of search | galal | Medium | Complete | 2018-03-08 | 2018-03-15 | 7
Courses |  |  | High | Complete | 2018-03-15 | 2018-03-29 | 14
course | analysis what courses have design the page with css implement the code testing the page | galal omer yasser yahia | High | Complete | 2018-03-15 | 2018-03-22 | 7
instructor | analysis info instructor design the instructor implement the instructor page testing | gaber amr abdallah yahia | Medium | Complete | 2018-03-22 | 2018-03-29 | 7
Entering to page |  |  | Medium | Complete | 2018-03-29 | 2018-04-19 | 21
login | analysis the login ,sign up design the login,SignUp implementthe login code implement the SignUp code test the login,SignUp effecint , database of login,SignUp backend | amr yahia amr abdallah gaber yasser galal | Medium | Complete | 2018-03-29 | 2018-04-05 | 7
signup |  |  | Medium | Complete | 2018-04-05 | 2018-04-12 | 7
database |  |  | Medium | Complete | 2018-04-12 | 2018-04-19 | 7
Help |  |  | Medium | Not Started | 2018-04-19 | 2018-04-29 | 10
ContactUs | analysis contact_us body | mohamedglal | Low | Not Started | 2018-04-19 | 2018-04-22 | 3
buy courses | analysis the way to buy course | amr abdallah yasser galal | Medium | Not Started | 2018-04-22 | 2018-04-25 | 3
logout | analysis how logout the website | yasser | Low | Not Started | 2018-04-25 | 2018-04-27 | 2
Aboutus | analysis the page content | mohamedgalal | low | Not Started | 2018-04-27 | 2018-04-29 | 3

## Sheet2
This sheet is to enable the drop-down lists
| High | Complete
| Medium | In Progress
| Low | Not Started